## Project management
# | Main Categories | SUB-CATEGORIES | GENERAL DESCRIPTION | CAUSES | CONSEQUENCE | LIKELIHOOD | IMPACT | Inherent Risk Rating | Existing Controls | Likelihood | Impact | Residual Risk Rating | MITIGATION | RISK ALLOCATION
|  | Project implementation | Delays in project delivery | a) Business continuity disruptions e.g Force majeure, pandemics b) Uncertainties in training completion c)Delays in external approvals | a) Additional project costs b) Contract expiration before project completion | 5 | 4 | 20 | a) Continuous project monitoring through Project Steering committee b) Alternative provisions for project continuity/Redundancies in the existing system c) Continous engagement with JICA experts d) Stakeholders engagement and management e) Liaise with security section for additional personnel | 3 | 3 | 9 | a) Develop a plan to use technology for security management b) Extension of ISMS coverage | Project Manager
|  |  | Stakeholder agitations/grievances e.g local community | a)Expectations due to past precedence set e.g Business opportunities b) Presumed inequalities from the community on jobs c) Leakage of information from internal sources e)Political influence | a) Project delays b) Disputes and litigations c) Project Disruptions d) Scope creep e) Reputation damage f) Increased costs | 5 | 4 | 20 | a)Weekly and monthly progress meetings b) Coordination with liaison office through Stakeholders Coordination Committee c) Awareness of staff policies d) Enforcement of employee code of conduct e) Continous engagement with stakeholders | 2 | 4 | 8 |  | Project Manager
|  |  | Scope creep( unplanned project activities) | a) Emerging stakeholder's needs b) Pandemic e.g COVID 19 c) Natural catastrophes i.e flooding, erosion d) Compliance with statutory guidelines e) Reliance on the third party infrastructure f) Vandalism of the existing infrastructure | a)Project delays | 5 | 4 | 20 | a)Multi-disciplinary and experienced Project Steering Committee b) Review of the scope by PTC c)Prior engagement of key stakeholders at the initial stage d) Continous engagement with stakeholders e)Virtual engagement meetings | 2 | 3 | 6 |  | Project Manager
|  |  | Change management | a) Lack of understanding of the system and expected benefits b) Resistance to change c) Lack of stakeholders engagement | a) Reputation damage b)Low uptake of the system c) Loss of management buy-in d) Failure to achieve corporate strategy( Digitization) e) Low returns on internal investment ( Value for money) | 4 | 4 | 16 | a) Continous Stakeholders engagement and management b) Technical and awareness training | 3 | 4 | 12 |  | Project Manager