## Instructions
TRANSPORTATION RISK ASSESSMENT TEMPLATE
riskpublishing.com ¦ Chris Ekai, ISO 31000 Lead Risk Manager
HOW TO USE THIS TEMPLATE
Work the Risk Register tab from left to right. It follows the five-step transportation risk assessment method: identify the hazard, analyze it (Likelihood x Impact), evaluate the score against your risk appetite, mitigate with controls, then monitor the residual risk and the action to closure.
Score every risk twice: once inherent (before new controls) and once residual (after your planned mitigation). The Score and Risk Level columns calculate automatically and colour themselves green, amber, or red. Five worked example rows are pre-filled, one per mode delete or overwrite them.
THE FIVE MODES TO COVER
1. Roadway driver fatigue, road geometry, traffic volume, weather, vehicle condition. 2. Airway flight operations, airport infrastructure, maintenance, emergency response. 3. Waterway vessel stability, navigation, collision probability, oil spill response. 4. Rail track integrity, bearing health, grade crossings, hazmat tank cars. 5. Pipeline corrosion, weld failure, leak detection, third-party excavation damage.
THE 5x5 SCORING MODEL
Likelihood and Impact are each rated 1 (very low) to 5 (very high). Risk Score = Likelihood x Impact, giving a 1 to 25 range. Bands: 1-4 Low (green), 5-9 Moderate (amber), 10-15 High (orange), 16-25 Extreme (red). See the Scoring Guide tab for the full scales and matrix.
U.S. REGULATORS BY MODE
FMCSA governs trucks and buses (hours of service, driver qualification, maintenance). FAA governs aviation. PHMSA governs pipelines and hazardous materials. FRA governs rail. The NTSB independently investigates serious accidents in every mode. Map each risk to the regulator that owns it.
REVIEW CADENCE
Re-assess whenever routes, cargo, vehicles, or regulations change and after any serious incident or near miss. Do not wait for the annual calendar. Log the review date and the next review date on every risk.
Companion guide: riskpublishing.com/transportation-risk-assessment/
(c) riskpublishing.com Free to use and adapt with attribution. Not legal or safety-engineering advice.

## Risk Register
TRANSPORTATION RISK ASSESSMENT RISK REGISTER
ID | Mode | Hazard / Risk Event | Cause / Source | Potential Consequence | Likelihood (1-5) | Impact (1-5) | Inherent Score | Inherent Level | Existing & Planned Controls | Residual Likelihood (1-5) | Residual Impact (1-5) | Residual Score | Residual Level | Risk Owner | Regulator | Target Date | Status
TR-01 | Roadway | Long-haul driver fatigue causes highway crash | Hours-of-service breach; night driving; tight schedule | Fatalities, injuries, cargo loss, FMCSA penalty | 4 | 5 | 20 | Extreme | Telematics fatigue alerts, ELD hours monitoring, trip scheduling, driver training | 2 | 5 | 10 | High | Fleet Safety Manager | FMCSA | 2026-09-30 | In progress
TR-02 | Airway | Ground handling damage undetected before departure | Rushed turnaround; inspection gap | Airworthiness incident, delay, injury | 2 | 5 | 10 | High | Pre-flight inspection checklist, FOD program, maintenance sign-off | 1 | 5 | 5 | Moderate | Aviation Safety Officer | FAA | 2026-10-31 | Open
TR-03 | Waterway | Vessel collision in congested port approach | Navigation error; poor visibility; traffic density | Hull breach, spill, casualties | 2 | 4 | 8 | Moderate | Bridge resource management, radar/AIS, pilot boarding, weather holds | 1 | 4 | 4 | Low | Marine Operations Lead | USCG / BTS | 2026-11-30 | Open
TR-04 | Rail | Overheated wheel bearing causes derailment with hazmat release | Bearing failure; detector spacing too wide | Derailment, toxic release, evacuation, >$1B cost | 3 | 5 | 15 | High | Wayside bearing detectors (lower thresholds), tank-car standards, route risk analysis | 1 | 5 | 5 | Moderate | Rail Safety Manager | FRA / NTSB | 2026-12-15 | In progress
TR-05 | Pipeline | Corrosion-driven pipeline leak of hazardous liquid | Material degradation; missed integrity dig | Environmental release, fines, property damage | 3 | 4 | 12 | High | Integrity management program, in-line inspection, leak detection, cathodic protection | 2 | 4 | 8 | Moderate | Pipeline Integrity Engineer | PHMSA | 2027-01-31 | Open

## Scoring Guide
SCORING GUIDE & 5x5 RISK MATRIX
Likelihood scale |  |  | Risk matrix Likelihood (rows) x Impact (columns) = score
Rating | Descriptor | Definition
1 | Rare | May occur only in exceptional circumstances | L \ I | 1 | 2 | 3 | 4 | 5
2 | Unlikely | Could occur at some time | 1 | 1 | 2 | 3 | 4 | 5
3 | Possible | Might occur occasionally | 2 | 2 | 4 | 6 | 8 | 10
4 | Likely | Will probably occur in most circumstances | 3 | 3 | 6 | 9 | 12 | 15
5 | Almost certain | Expected to occur in most circumstances | 4 | 4 | 8 | 12 | 16 | 20
|  |  | 5 | 5 | 10 | 15 | 20 | 25
Impact scale
Rating | Descriptor | Definition
1 | Insignificant | No injury; negligible cost or delay | 1 2 3 4 5: Risk bands
2 | Minor | First aid; small cost; minor delay | 1 2 3 4 5: Score; 1 2 3 4 5: Level; 2 4 6 8 10: Response
3 | Moderate | Medical treatment; notable cost; SLA breach | 1 2 3 4 5: 1-4; 1 2 3 4 5: Low; 2 4 6 8 10: Monitor; manage by routine procedures
4 | Major | Serious injury; large cost; regulatory fine | 1 2 3 4 5: 5-9; 1 2 3 4 5: Moderate; 2 4 6 8 10: Specific management responsibility; plan controls
5 | Catastrophic | Fatality; major loss; license or hazmat event | 1 2 3 4 5: 10-15; 1 2 3 4 5: High; 2 4 6 8 10: Senior attention; act promptly
|  |  | 16-25 | Extreme | Immediate action; escalate to leadership