## 281df360cf968bed
System Name | System Owner | Validation Status | Risk Description | Source of Risk | Impact | Likelihood | Severity | RPN | Existing Controls | Control Effectiveness | Residual Risk | Action Plans | Responsible | Deadline | Monitoring Method | Review Frequency | Next Review Date
Sys 1 | John Doe | Validated | Risk of data loss | Software | Data Integrity | Medium | Major | 60 | Regular backups | Strong | Low | Increase backup frequency Implement cloud storage | Jane Smith | 31/12/2024 | System Audit | Quarterly | 30/06/2024
Sys 2 | Emily Chen | Under Validation | Unauthorized access risk | Network | Data Security | High | Major | 80 | Firewalls, Access Controls | Adequate | Medium | Enhance network security Regular security training | Bob Lee | 31/03/2024 | Network Monitoring | Bi-annually | 31/12/2024
Sys 3 | Michael Brown | Validated | Risk of system downtime | Hardware | Operational | High | Moderate | 60 | Redundant systems | Adequate | Medium | Scheduled maintenance Upgrade hardware | David Wilson | 30/04/2024 | Operational Review | Annually | 31/07/2024
Sys 4 | Sarah Johnson | Under Validation | Compliance risk | Regulatory | Compliance | Medium | Major | 60 | Compliance checks | Poor | High | Compliance training Audit trail implementation | Frank Miller | 31/05/2024 | Compliance Audits | Quarterly | 30/04/2024
Sys 5 | Daniel Lee | Validated | Data corruption risk | Software | Data Integrity | Low | Major | 40 | Data validation checks | Strong | Low | Implement checksums Increase data redundancy | Henry Kim | 30/06/2024 | Data Integrity Checks | Monthly | 31/05/2024
Sys 6 | Olivia Smith | Under Validation | Risk of inaccurate data | User Input | Data Accuracy | Medium | Moderate | 45 | Input validation | Adequate | Medium | User training Enhance validation rules | Jack Taylor | 31/07/2024 | Quality Assurance | Bi-annually | 31/10/2024
Sys 7 | Noah Wilson | Validated | Risk of outdated software | Software Update | Operational | Low | Moderate | 20 | Regular updates | Strong | Low | Implement auto-update Software review process | Kevin Brown | 30/09/2024 | Software Review | Annually | 31/08/2024
Sys 8 | Emma Johnson | Under Validation | Security breach risk | Cyber Attack | Data Security | High | Major | 80 | Encryption, Intrusion Detection | Adequate | Medium | Enhance intrusion detection Cybersecurity training | Mike Davis | 31/10/2024 | Security Monitoring | Quarterly | 31/01/2025
Sys 9 | Liam Davis | Validated | Risk of hardware failure | Hardware | Operational | Medium | Major | 60 | Hardware maintenance | Adequate | Medium | Upgrade critical hardware Implement redundancy | Oscar Hernandez | 31/12/2024 | Hardware Inspection | Bi-annually | 30/06/2024
Sys 10 | Sophia Martinez | Under Validation | Risk of non-compliance | Regulatory | Compliance | High | Major | 80 | Compliance monitoring | Poor | High | Review compliance policies Staff compliance training | Rachel Kim | 30/11/2024 | Compliance Review | Annually | 31/03/2025
Sys 11 | Mason Lee | Validated | Risk of data breach | External Threat | Data Security | High | Major | 80 | Security protocols | Adequate | Medium | Enhance data encryption Regular security audits | Tina Brown | 31/01/2025 | Security Audits | Quarterly | 31/12/2024