## bf2099a1662735f3
Risk ID | Risk Description | Asset | Threats | Vulnerabilities | Likelihood | Impact | Risk Level | Existing Controls | Control Effectiveness | Residual Risk | Additional Controls Needed | Action Owner | Target Date
1 | Unauthorized data access | Customer Database | Hacking attempts | Inadequate firewall | Medium | High | High | Firewall, Access Controls | Partially Effective | Medium | 1. Implement advanced firewall. 2. Enhance user authentication protocols. | IT Manager | 2024-06-30
2 | Data loss | Employee Records | System failure | Outdated backup system | Low | High | Medium | Regular backups | Effective | Low | 1. Upgrade backup system. 2. Implement off-site backups. | IT Manager | 2024-03-31
3 | Phishing attacks | Email System | Phishing emails | Lack of employee awareness | High | Medium | High | Email filters | Partially Effective | Medium | 1. Conduct regular security awareness training. 2. Implement advanced email filtering solutions. | Security Officer | 2024-05-15
4 | Malware infection | Internal Network | Malware | Outdated antivirus software | Medium | High | High | Antivirus software | Partially Effective | Medium | 1. Update antivirus software. 2. Regular malware scanning protocols. | IT Security | 2024-04-20
5 | Insider threat | Financial Data | Disgruntled employee | Insufficient access controls | Medium | High | High | Access level controls | Effective | Medium | 1. Regular access reviews. 2. Implement behavior monitoring systems. | HR Manager | 2024-07-10
6 | Service downtime | Online Services | DDoS attack | Inadequate DDoS protection | High | High | High | DDoS protection measures | Partially Effective | High | 1. Enhance DDoS mitigation tools. 2. Develop a business continuity plan. | Operations Manager | 2024-08-25
7 | Data integrity issues | Database Systems | Unauthorized changes | Lack of change control | Medium | Medium | Medium | Change management process | Effective | Low | 1. Implement automated integrity checks. 2. Strengthen change approval process. | Database Administrator | 2024-09-30
8 | Legal compliance breach | Record Keeping | Non-compliance | Outdated legal knowledge | Low | High | Medium | Compliance audits | Effective | Low | 1. Regular legal training for staff. 2. Update compliance policies. | Compliance Officer | 2024-10-15
9 | Physical security breach | Office Premises | Unauthorized access | Poor physical security | Medium | Medium | Medium | Physical access controls | Effective | Medium | 1. Upgrade security systems. 2. Increase security personnel. | Facilities Manager | 2024-11-20
10 | Cloud data breach | Cloud Storage | Hacking | Weak cloud security measures | High | High | High | Cloud security protocols | Partially Effective | High | 1. Strengthen cloud access controls. 2. Regular security audits of cloud infrastructure. | Cloud Services Manager | 2024-12-31