## c54a78688925da95
Change ID | Assessment Date | Change Description | Risk Category | Risk Description | Potential Impact | Likelihood of Occurrence | Current Controls | Recommended Mitigation Actions | Responsible Party | Review Date
CHG001 | 2024-01-22 | Upgrade of CRM system | System Stability | Potential system downtime during the upgrade | High | Medium | Backup and rollback plan | Schedule during low-traffic hours | IT Operations Manager | 2024-02-01
CHG002 | 2024-01-22 | Implementation of new firewall | Security | Risk of temporary security vulnerabilities | High | High | Security testing protocol | Enhanced monitoring post-implementation | Security Manager | 2024-02-15
CHG003 | 2024-01-22 | Migration to cloud storage | Compliance | Data compliance issues with new provider | Medium | Medium | Compliance review process | Detailed compliance audit of provider | Compliance Officer | 2024-03-01
CHG004 | 2024-01-22 | Update of network infrastructure | Network Stability | Risk of network disruption | High | High | Network monitoring systems | Gradual rollout of network updates | Network Administrator | 2024-03-15
CHG005 | 2024-01-22 | Deployment of new software | User Training | Staff unprepared for new software | Medium | Medium | Training sessions planned | Additional hands-on training sessions | Training Coordinator | 2024-04-01
CHG006 | 2024-01-22 | Data center relocation | Operational Risk | Risk of extended downtime during relocation | High | High | Detailed relocation plan | Assign dedicated relocation team | Data Center Manager | 2024-04-15
CHG007 | 2024-01-22 | Introduction of BYOD policy | Security | Increased risk of data breaches | High | Medium | BYOD security policy | Regular security awareness training | IT Security Analyst | 2024-05-01
CHG008 | 2024-01-22 | Server virtualization project | Technical Stability | Technical issues during virtualization | Medium | Medium | Virtualization test environment | Phased virtualization approach | Systems Engineer | 2024-05-15
CHG009 | 2024-01-22 | Upgrade of email system | System Compatibility | Compatibility issues with existing systems | Low | Medium | Compatibility testing | Pilot testing with a user group | IT Support Manager | 2024-06-01
CHG010 | 2024-01-22 | Implementation of ERP system | Integration Risk | Challenges in integrating with existing systems | High | High | Integration testing protocol | Engage integration specialists | ERP Project Manager | 2024-06-15