## db118fb802df4d68
Project ID | Assessment Date | Product Name | Risk Factor | Description of Risk | Potential Impact | Likelihood of Occurrence | Current Controls | Recommended Mitigation Actions | Responsible Party | Review Date
1 | 2024-01-22 | Product A | Manufacturing Process | Use of nitrite in processing may lead to nitrosamine formation | High | Medium | Strict process control | Review and modify processing methods | Quality Assurance | 2024-06-01
2 | 2024-01-22 | Product B | Raw Materials | Potential contamination of raw materials with nitrosamines | Medium | Low | Supplier quality checks | Implement additional testing protocols | Procurement Manager | 2024-06-15
3 | 2024-01-22 | Product C | Storage Conditions | Improper storage leading to increased nitrosamine levels | Low | Low | Controlled storage environment | Enhance storage monitoring | Logistics Manager | 2024-07-01
4 | 2024-01-22 | Product D | Packaging Materials | Packaging materials may contribute to nitrosamine risk | Medium | Medium | Quality control of packaging | Source alternative packaging materials | Packaging Department | 2024-08-01
5 | 2024-01-22 | Product E | Cross-contamination | Risk of cross-contamination during production | High | High | Segregated production lines | Introduce additional cleaning protocols | Production Manager | 2024-08-15
6 | 2024-01-22 | Product F | Chemical Reactions | Chemical reactions during processing leading to nitrosamines | High | Medium | Monitoring chemical levels | Adjust processing parameters | Process Development | 2024-09-01
7 | 2024-01-22 | Product G | Temperature Control | Elevated temperatures increasing nitrosamine formation | Medium | Low | Temperature monitoring | Implement stricter temperature controls | Quality Control | 2024-09-15
8 | 2024-01-22 | Product H | Supplier Practices | Supplier handling practices may introduce nitrosamines | Medium | Medium | Supplier audits | Enhanced supplier training and guidelines | Supplier Management | 2024-10-01
9 | 2024-01-22 | Product I | Equipment Contamination | Contamination from manufacturing equipment | Low | Medium | Regular equipment cleaning | Upgrade to specialized equipment | Equipment Maintenance | 2024-10-15
10 | 2024-01-22 | Product J | Final Product Testing | Inadequate testing of final product for nitrosamines | High | High | Standard product testing | Implement more rigorous testing methods | Quality Assurance | 2024-11-01