## 043666e775fd04fb(1)
Project ID | Assessment Date | Risk Category | Risk Description | Potential Impact | Likelihood of Occurrence | Current Controls | Recommended Mitigation Actions | Responsible Party | Review Date
101 | 2024-01-22 | Safety | Risk of accidents due to inadequate safety measures | High | High | Standard safety protocols | Implement enhanced safety training | Safety Manager | 2024-02-15
102 | 2024-01-22 | Environmental | Potential environmental impact due to waste disposal | Medium | Medium | Waste management plan | Develop a more sustainable waste plan | Environmental Officer | 2024-02-20
103 | 2024-01-22 | Financial | Risk of budget overruns due to unforeseen costs | High | Medium | Budget contingency plan | Regular financial audits | Finance Department | 2024-02-18
104 | 2024-01-22 | Legal | Risk of non-compliance with construction regulations | High | Medium | Compliance checks in place | Increase legal oversight | Legal Department | 2024-03-10
105 | 2024-01-22 | Operational | Delays in project timeline due to supplier issues | Medium | High | Supplier agreements | Establish alternative suppliers | Operations Manager | 2024-03-05
106 | 2024-01-22 | Technical | Risk of technical failures in construction equipment | Medium | Low | Equipment maintenance plan | Upgrade to more reliable equipment | Technical Supervisor | 2024-03-20