## pre construction risk assessmen
Risk ID | Risk Description | Risk Category | Likelihood | Impact | Risk Level | Mitigation Measures
1 | Delay in material supply | Supply Chain | High | Medium | High | Establish alternative suppliers
2 | Increase in material cost | Financial | Medium | High | Medium | Lock in prices with suppliers
3 | Weather-related delays | Environmental | High | High | High | Schedule flexible work plans
4 | Labor shortages | Human Resource | Medium | High | Medium | Develop a backup labor plan
5 | Safety incidents | Safety | Low | High | Medium | Implement rigorous safety protocols
6 | Permit and regulatory delays | Legal | Medium | Medium | Medium | Engage early with authorities
7 | Technical design flaws | Technical | Low | High | Medium | Conduct thorough design reviews
8 | Stakeholder opposition | Stakeholder | Medium | Medium | Medium | Develop a stakeholder engagement plan